## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone 1: Tabletop tablet selection and vendors
1.1 Research and sign a contract to develop a user friendly menu software system |  |  |  | 2 day | Peta | bar: WEEK 1 M to WEEK 1 T
1.2 Research vendor and order tablet brand compatible with the requirements for Sauce & Spoon menu system |  |  |  | 7 days | Seydou | bar: WEEK 1 W to WEEK 2 R
1.3 Generate quotes and review costs for tablets and electrician vendors |  |  |  | 2 day | Peta | bar: WEEK 2 F to WEEK 3 M
1.4 Choose and purchase tablet brand |  |  |  | 2 day | Peta | bar: WEEK 3 T to WEEK 3 W
1.5 Create contracts and statements of work for vendors |  |  |  | 2 days | Peta | bar: WEEK 3 R to WEEK 3 F
Milestone 2: Finalize tablet software development, installation and test it
2.1 Organize a meeting for the menu photoshoot with the photographer |  |  |  | 1 hour | Deanne | bar: WEEK 4 M
2.2 Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  |  |  | 1 day | Seydou | bar: WEEK 4 T
2.3 Delivery of tablets and a check up if tablets compatible with current POS software |  |  |  | 11 days | Seydou | bar: WEEK 4 T to WEEK 6 M
2.4 Install Cross-promotional feature on tablets that pair menu items and add-ons |  |  |  | 2 days | Peta | bar: WEEK 5 F to WEEK 6 M
2.5 Installation of the tablets on Downtown and North restaurant location |  |  |  | 2 days | Peta | bar: WEEK 6 T to WEEK 6 W
2.6 Try the new system and test if it is working and easy to use |  |  |  | 2 days | Peta | bar: WEEK 6 R to WEEK 6 F
Milestone 3: Training sessions and a try run of the menu system
3.1 Organize a meeting with the staff at the restaurants in the North and Downtown location to introduce the new ordering system |  |  |  | 1 hours | Peta | bar: WEEK 7 M
3.2 Schedule training sessions |  |  |  | 2 hours | Peta | bar: WEEK 7 T to WEEK 7 W
3.3 Organize training sesions with the Director of operations and general managers staff |  |  |  | 4 hours | Alex | bar: WEEK 7 W to WEEK 7 R
3.4 Training of the servers and the kichen staff |  |  |  | 8 hours | Seydou | bar: WEEK 7 F to WEEK 8 T
Milestone 4: Finalization of the tabletop menu setup and launch
4.1 Test the tabletop menu system with family and friends before lauch |  |  |  | 6 hours | Deanne | bar: WEEK 10 M
4.2 Develop a troubleshoot cheatsheet for emergancies |  |  |  | 1 day | Peta | bar: WEEK 10 T
4.3 Include customer satisfaction survey in the tabletop menu |  |  |  | 1 day | Peta | bar: WEEK 10 W
4.4 Lauch day |  |  |  | 1 day | Peta | bar: WEEK 10 R
4.5 Conitnues update of the software menu |  |  |  | 1 day | Deanne | bar: WEEK 10 F
Schedule a test run on family & friends |  |  |  | 1 day
Get feedback from test run |  |  |  | 4 hours
troubleshoot tablet issues from test run |  |  |  | 2 days
Launch Tablets |  |  | 2023-02-05
Swap to newer tablest |  |  |  | 30 min

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Choose a tablet vendor | researching tablet features compare tablet pricing confirming compatible operating systems
Schedule an electrician | Hire electrician Wiring to charge tablets Write up vendor contracts & SoW | 2 days |  |  |  | M
Staff meetings with GMs | Schedule meetings to discuss waitstaff tips Get staff buy-in on tablets
Order Tablets | Account for shipping delays and broken devices 11 days to ship 2-3 for delays | 14 days
Set up tablet Software | Need to be able to update the menu in realtime Update POS system Have security features installed on tablets Add a post-dining customer service survey | 3 days |  |  |  | M
Install tablets | Install tablets in bar areas for the Downtown & North restaurant locations
Software Training - General Managers | Schedule small group of management | 1 day
Software Training - Waitstaff | Managers will trian waitstaff | 2 days
Test Run of training & tablets | Invite friends and family to test the tablets Gather feedback from test run | 1 day
Troubleshoot tablet | acknowledge good & back from test run & fix any issues before the launch
Launch Tablets | [6 empty] | 2023-04-01
Swap to new tablets | a month after the launch | 30 days

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Tabletop tech speeds up service and boosts profits, study says | https://www.restaurantdive.com/news/tabletop-tech-speeds-up-service-and-boosts-profits-study-says/560152/ | 2022-08-26 | Internet security needs addressed
How to Develop a Successful POS System Implementation Plan | https://www.talech.com/blog/2020/05/07/resources-how-to-develop-a-successful-pos-system-implementation-plan/ | 2022-08-26 | There is a list of Benefits with simple steps

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Average ticket time | Average table turn time is down by 30 min | Does the revenue increases with the table turn time being reduced? | 5% revenue increase compared to previous year | FALSE
Check-out process | One minute or less | Do customer find the tablet experience and checkout experience user-friendly? | level of customer satisfacation from the tablet experience | FALSE
Tablet experience | less than 5% of clients report technical issues in a week | What can cause the technical issues with tablets? | number of errors- type of technical issues that arise and effect the tablet experience | FALSE
Cutting down incorrect orders | 98% order accuracy | What can be done to reduce cutting down orders to minimum? | 2% of error- type of errors that lead to cutting down orders | FALSE
Customer wait time in the lobby | Average wait time is 10 min or less | Did the number of people increased in the lobby with the faster table turn time? | Optimal number of waiting guests- Did the number of visitors increased so much, that the waiting time doesn't necessarary decrease. | FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average table turn time is down by 30 min | Does the revenue increases with the table turn time being reduced? | 5% revenue increase compared to previous year | Did the dinner took less time that usually? | Yes/No | Yes | No
Check out process is one minute or less | Do customer find the tablet experience and checkout experience user-friendly? | level of customer satisfacation from the tablet experience | On scale 1-5 (where 1 is very dissatisfied and 5 is very satisfied) how satisfied are you with your tablet experience? | Scaled | Very dissatisfied | Somewhat dissatisfied | Neither dissatisfied nor satisfied | Somewhat satisfied | Very satisfied
Tablet experience- less than 5% of clients report technical issues in a week | What can cause the technical issues with tablets? | number of errors- type of technical issues that arise and effect the tablet experience | Do you find that ordering via tablet is better that telling your order to a waiter? | True/False | TRUE | FALSE
98% order accuracy | What can be done to reduce cutting down orders to minimum? | 2% of error- type of errors that lead to cutting down orders | Did the tablet offer all the features you need to place your desired order? If not, what feature are you missing? | Open-ended | open-ended
Average wait time is 10 min or less | Did the number of people increased in the lobby with the faster table turn time? | Optimal number of waiting guests- Did the number of visitors increased so much, that the waiting time doesn't necessarary decrease. | How long are you ready to wait before getting seated? | Multiple choice | I am not ready to wait at all | I am ready to wait up to 5 min | I am ready to wait from 5 to 10 min | I am ready to wait as lomg as it takes | Other
|  |  | On a scale 1-5 (where 1 is very dissatisfied and 5 is very satisfied) how satisfied are you with the payment process via the tablet? | Scaled | Very dissatisfied | Somewhat dissatsified | Neither dissatisfied nor satisfied | Somewhat satisfied | Very satisfied
|  |  | Was your first order via the tablet clear and easy? | Yes/No | Yes, it was clear | No, I asked waiter to help
|  |  | Would you prefer ordering via the tablet next time again? | Multiple choice | Yes, defintely | Yes, but I would like to consult the waiter as well | No, never again | Other
|  |  | Would you like to provide anym additional feedback on your tablet experience? | Open-ended | open-ended question