## Sheet1
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone 1: Launch Project
Align with stakeholders |  |  |  | 3 hours
Summarize projections and enhancements |  |  |  | 5 days
Interview staffs |  |  |  | 2 hours
Create share documents |  |  |  | 2 hours
Set up kick off meeting |  |  |  | 1 day
Milestone 2: Tablet Purchase
Research tablet opoints |  |  |  | 3 hours
Generate quotes and review
Choose a tablet vendor and phrchase system |  |  |  | 1 day
Create contracts and statements of work for vendors |  |  |  | 3 months
Align vendor timeline and installation |  |  |  | 2 days
Project Plan Updates |  |  |  | 3 hours
Milestone 3: Tablet & Software Installation
Hire an electrician to wire tables for tablets |  |  |  | 1 day
Install Tablets and software |  |  |  | 3 days
Finish the test |  |  |  | 1 day
Milestone 4: Configure tablet to POS system
Finalize menu & coupon values |  |  |  | 8 hours
Upload menu and coupon values |  |  |  | 8 hours
Milestone 5: Training Program for employees
Make a training plan |  |  |  | 8 hours
Create a training program |  |  |  | 1 day
Schedule training lessons |  |  |  | 8 hours
Train waitstaff |  |  |  | 1 day
Document changes |  |  |  | 8 hours
Milestone 6: Launch Preperation
Update on website and social media plan |  |  |  | 8 hours
Create launch day |  |  |  | 8 hours
Schedule a dry run with friends before official launch |  |  |  | 8 hours
Milestone 7: Launch Day
Official launch |  |  |  | 8 hours
Keep on track about the feedback |  |  |  | 8 hours
Project milestones
Project Name | Training Waitress
Project Task | Time/Month
| Sep | Oct | Nov
Schedule a training for a small group of manager at each location
Schedule staff meetings with GM to discuss anything that could affect waitstaff tips
invite friends and family to do a test run of the tables