## Product Backlog
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone 1: Launch Project
Align with stakeholders |  |  |  | 3 hours | Peta | Completed
Summarize projections and enhancements |  |  |  | 5 days | Alex | Pending
Interview staffs |  |  |  | 2 hours | Gilly | Pending
Create share documents |  |  |  | 2 hours | Seydou | Pending
Set up kick off meeting |  |  |  | 1 day | Peta | Completed
Milestone 2: Tablet Purchase
Research tablet opoints |  |  |  | 3 hours | Vendor | Completed
Generate quotes and review
Choose a tablet vendor and phrchase system |  |  |  | 1 day | Gilly | Completed
Create contracts and statements of work for vendors |  |  |  | 3 months | Seydou | Pending
Align vendor timeline and installation |  |  |  | 2 days | Peta | Pending
Project Plan Updates |  |  |  | 3 hours | Vendor | Pending
Milestone 3: Tablet & Software Installation
Hire an electrician to wire tables for tablets |  |  |  | 1 day | Peta | Pending
Install Tablets and software |  |  |  | 3 days | Alex | Completed
Finish the test |  |  |  | 1 day
Milestone 4: Configure tablet to POS system
Finalize menu & coupon values |  |  |  | 8 hours | Alex | Pending
Upload menu and coupon values |  |  |  | 8 hours | Seydou | Completed
Milestone 5: Training Program for employees
Make a training plan |  |  |  | 8 hours | Gilly | Pending
Create a training program |  |  |  | 1 day | Seydou | Pending
Schedule training lessons |  |  |  | 8 hours | Peta | Completed
Train waitstaff |  |  |  | 1 day | Alex | Completed
Document changes |  |  |  | 8 hours
Milestone 6: Launch Preperation
Update on website and social media plan |  |  |  | 8 hours | Gilly | Pending
Create launch day |  |  |  | 8 hours | Seydou | Pending
Schedule a dry run with friends before official launch |  |  |  | 8 hours | Peta | Pending
Milestone 7: Launch Day
Official launch |  |  |  | 8 hours | Seydou | Completed
Keep on track about the feedback |  |  |  | 8 hours | Peta | Completed

## Sprint Backlog
Epic | User Story Title | Story | Acceptance Criteria | Value | Estimate (Story Points) | Current Sprint | Sprints
Plant Care Initiatives | Low-maintenance options | As a potential customer, I want to find out which plants are easiest to care for so that I can purchase low-maintenance options. | 1) Ability to sort plants by "beginner," "intermediate," and "advanced" 2) Ability to search for plants with similar care needs | $$$ | 8 | 52 | Name | Current Sprint | Next Sprint
Plant Care Initiatives | Plant care tips | As a plant owner, I want to access care instructions easily so that I can keep my plant alive longer. | 1) Receive plant care leaflet with each order 2) Option to sign up for monthly emails with seasonal care tips | $$$ | 8 | 44 | Start date | 2021-03-01 | 2021-03-22
Plant Care Initiatives | Plant care tools | As a plant owner, I want to have the right tools to care for my plant so that I can keep it healthy and beautiful. | 1) Can purchase plant care starter kits (for ferns, succulents, vines, etc.) 2) Option to buy partial kits or single tools | $$ | 13 | 31 | End date | 2021-03-19 | 2021-04-09
Plant Care Initiatives | Watering reminders | As a plant owner, I want to remember when to water my plants so that I don't under- or overwater them. | 1) Option to sign up for reminder texts or emails 2) Option to add reminder stickers for use with calendars to each order | $$ | 5 | 26 | Point Capacity | 0 | 0
Plant Care Initiatives | Return policy | As a customer, I want a hassle-free way to return my order so that I can be sure I have the right plant for me. | 1) Credit and return FAQ linked on homepage 2) All orders ship with return labels and instructions | $$ | 5 | 21 | Points Assigned | #VALUE! | #VALUE!
Plant Care Initiatives | Expert help & advice | As a plant owner, I want to get expert help and advice quickly so that I know what to do if my plant gets sick. | 1) Access to live chat support 2) Longer phone support hours | $ | 8 | 13 | Value Attributed | #VALUE! | #VALUE!
Bonsai Trees | Bonsai Selection | As a potential customer, I want to be able to select from a variety of different Bonsai trees so that I can pick the exact type I want. | 1) Ability to select from multiple tree species 2) Options to sort by species, size, and care requirements | $$$ | 13 | 0